## Tabelle1
Sprint Review Protocol
Sprint No: |  | 2
Date & Time |  | 29.03.2023 - 18.04.2023
Group Number |  | Gruppe 16
Participant 1 |  | Heider, Simon
Participant 2 |  | Neuhold, Paul, Jakob
Participant 3 |  | Petkovic, Vladan
Participant 4 |  | Tavaszi, Peter
Participant 5 |  | -
Mentor |  | Oswald
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Pizza-Button | 2 | 3 | 1 | 1
2 | Website-Layout | 2 | 5 | 3 | 1
3 | Willkommensmodal | 0.5 | 0.5 | 0 | 1
4 | Spiel-Logik, Spieldesign | 4 | 4.5 | 0.5 | 1
5 | Statistiken berechnen und anzeigen | 3 | 3 | 0 | 1
6 | Spiel-Logik, Spieldesign von Level 2 entwickeln | 2 | 2 | 0 | 1
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | 4.5 | 6 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol