## Tabelle1
Sprint Review Protocol
Sprint No: |  | 3
Date & Time |  | 03.05.2023 - 16.05.2023
Group Number |  | Gruppe 16
Participant 1 |  | Heider, Simon
Participant 2 |  | Neuhold, Paul, Jakob
Participant 3 |  | Petkovic, Vladan
Participant 4 |  | Tavaszi, Peter
Participant 5 |  | -
Mentor |  | Oswald
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Spieldesign Level 3 | 8 | 8 | 0 | 1
2 | Browser Tab Icon | 0.5 | 0.25 | -0.25 | 1
3 | Failsafe-Überarbeitung | 2 | 2 | 0 | 1
4 | Code-Überarbeitung | 3 | 6.25 | 3.25 | 1
5 | Level-wincondition | 2 | 2 | 0 | 1
6 | Level-2-3-Modal | 1 | 1.25 | 0.25 | 1
7 | Github-branches | 2 | 5 | 3 | 1
8 | Werbung | 3 | 4 | 1 |  | 1
9 | Nachfrage | 6 | 4 | -2 |  | 1
10 | Preise ändern | 4 | 5 | 1 |  | 1
11 | Resümee Level-3 | 2 | 5 |  | 1
11 |  |  |  | 6.25 | 8 | 3
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol