## Tabelle1
Sprint Review Protocol
Sprint No: |  | 5
Date & Time |  | 17.05.2023 - 30.05.2023
Group Number |  | Gruppe 16
Participant 1 |  | Heider, Simon
Participant 2 |  | Neuhold, Paul, Jakob
Participant 3 |  | Petkovic, Vladan
Participant 4 |  | Tavaszi, Peter
Participant 5 |  | -
Mentor |  | Oswald
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Bestellungen | 4 | 7 | 3 | 1
2 | Random-Events | 5 | 6 | 1 | 1
3 | Pizza-Machine Bugfix | 1 | 1 | 0 | 1
4 | setLevel() Bugfix | 2 | 2 | 0 | 1
5 | Nachfrage | 1 | 1 | 0 | 1
6 | Level-4 planen | 6 | 10 | 4 | 1
7 | Github-branches | 4 | 4 | 0 | 1
8 | Werbung | 4 | 7 | 3 | 1
9 | Code-Testen bis inkl. Level 3 | 4 | 2 | -2 | 1
10 | Resümee Sprint 5 | 4 | 4 | 0 | 1
10 |  |  |  | 9 | 10 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol