## Tabelle1
Sprint Review Protocol
Sprint No: |  | 7
Date & Time |  | 14.06.2023 - 27.06.2023
Group Number |  | Gruppe 16
Participant 1 |  | Heider, Simon
Participant 2 |  | Neuhold, Paul, Jakob
Participant 3 |  | Petkovic, Vladan
Participant 4 |  | Tavaszi, Peter
Participant 5 |  | -
Mentor |  | Oswald
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | User manual | 3 | 4.5 | 1.5 | 1
2 | deployment manual | 3 | 4 | 1 | 1
3 | Leaderboard | 10 | 13 | 3 | 1
4 | Code-Meetings | 40 | 48 | 8 | 1
5 | Bugs und Anpassungen | 30 | 21.5 | -8.5 | 1 |  | summary of all bugs and corrections as one topic
6 | Präsentationsvideo | 10 | 11 | 1 | 1
6 |  |  |  | 6 | 6 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol